## Estimate Summary
INFORMATICS - ESTIMATE SUMMARY
Track |  | Employee | Contractor | Consultant | Comments
|  | Cost | Cost | Cost
Data Integration/Engineering |  | 15912 | 18720 | 28080
Reporting |  | 35890.4 | 42224 | 63336
MDM / RDM |  | 0 | 0 | 0
Data Quality |  | 0 | 0 | 0
TOTAL |  | 51802.4 | 60944 | 91416
Business Analyst + Scrum Master | 10 | 2590.12 | 3047.2 | 4570.8 | Hrs / Week
Oversight (Informatics Delivery Lead) | 10% | 5180.24 | 6094.4 | 9141.6 | Update % if required
Platform Architecture / Design Review | 4 | 340 | 400 | 600 | Total Hrs required (Min. 4 Hrs per Area)
Platform Support | 4 | 340 | 400 | 600 | Total Hrs required
TOTAL - PROJECT DELIVERY |  | 60252.76 | 70885.6 | 106328.4
ON-GOING COST
Labor : On-going Cost (First Year) | 10% | 5180.24 | 6094.4 | 9141.6
Non-Labor : Storage/Compute (First Year) | 10% | 5180.24 | 6094.4 | 9141.6
Non-Labor : Tableau (First Year)
Platform Support : On-going Cost (First Year) | 10 | 850 | 1000 | 1500 | Total Hrs required
TOTAL - FIRST YEAR |  | 71463.24 | 84074.4 | 126111.6
Labor : On-going Cost (Year 2) |  | 5180.24 | 6094.4 | 9141.6
Non-Labor : Storage/Compute (First Year)
Non-Labor : Tableau (First Year)
Platform Support (On-going Cost - Year 2) | 20 | 1700 | 2000 | 3000 | Total Hrs required
TOTAL - SECOND YEAR |  | 6880.24 | 8094.4 | 12141.6
Labor : On-going Cost (Year 3) |  | 5180.24 | 6094.4 | 9141.6
Non-Labor : Storage/Compute (First Year)
Non-Labor : Tableau (First Year)
Platform Support (On-going Cost - Year 3) | 20 | 1700 | 2000 | 3000 | Total Hrs required
TOTAL - THIRD YEAR |  | 6880.24 | 8094.4 | 12141.6

## Estimate Work Sheet
INFORMATICS - ESTIMATE WORK SHEET
Project Methodology | Waterfall | Agile | Weeks - Waterfall | Weeks - Agile | Team Size - Waterfall | Team Size - Agile | Duration - Waterfall | Duration - Agile
Analysis / Design | 243.776 | 60.944 | 6.0944 | 1.5236 | 5 | 5 | 1.2189 | 0.30472
Build / Design | 121.888 | 304.72 | 3.0472 | 7.618 | 5 | 5 | 0.60944 | 1.5236
Testing | 243.776 | 243.776 | 6.0944 | 6.0944 | 5 | 5 | 1.2189 | 1.2189
TOTAL Hrs | 609.44 | 609.44 | 15.236 | 15.236 | 15 | 15 | 3.0472 | 3.0472
Work Item | Standard Effort |  |  |  |  | Quantity |  |  |  |  | Weighted Estimation | [6 empty] | Employee | Contractor | Consultant
| Very Simple (Effort) | Simple (Effort) | Medium (Effort) | Complex (Effort) | Scale Reduction (Very Simple) | Very Simple (Count) | Simple (Count) | Medium (Count) | Complex (Count) | Total Hours | Optimistic (20% less than likely) | Optimistic Weight | Likely | Likely Weight | Pessimistic (20% more than likely) | Pessimistic Weight | Weighted Hours | 85 | 100 | 150
Data Integration/Engineering
EDW - Data Ingestion - Foundation | 40 | 160 | 240 | 360 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Extraction from Databases / EDW - Custom Data Feeds | 20 | 120 | 180 | 300 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Data Ingestion - Raw / Data Lake (easyETL) | 8 | 16 | 24 | 48 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Data Ingestion - Raw / Data Lake (CUSTOM) | 40 | 100 | 160 | 200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Data Ingestion - Standard | 80 | 160 | 240 | 360 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Data Ingestion - Aggregate | 80 | 120 | 180 | 280 | 100% | 0 | 0 | 1 | 0 | 180 | 144 | 1 | 180 | 6 | 216 | 3 | 187.2 | 15912 | 18720 | 28080
Data Ingestion - Distribution | 80 | 100 | 140 | 240 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Custom Data Extraction (From IE) | 40 | 160 | 260 | 360 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
MuleSoft API | 40 | 80 | 120 | 200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Sandbox - Views / Direct Data Load in PROD Sandbox | 2 | 4 | 8 | 16 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Subtotal | [5 empty] | 0 | 0 | 1 | 0 | 180 | 144 |  | 180 |  | 216 |  | 187.2 | 15912 | 18720 | 28080
Reporting
Reporting - Sematic Data Layer | 0 | 44 | 66 | 88 | 100% | 0 | 0 | 1 | 0 | 66 | 52.8 | 1 | 66 | 6 | 79.2 | 3 | 68.64 | 5834.4 | 6864 | 10296
Reporting - Data Cubes | 0 | 130 | 180 | 260 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Reporting Presentation Layer - Dashboard | 0 | 130 | 160 | 180 | 100% | 0 | 0 | 1 | 0 | 160 | 128 | 1 | 160 | 6 | 192 | 3 | 166.4 | 14144 | 16640 | 24960
Reporting Presentation Layer - Reports | 0 | 110 | 130 | 150 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Reporting Presentation Layer - Adhoc Report | 0 | 60 | 80 | 100 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Reporting Web UI Customization | 0 | 100 | 180 | 260 | 100% | 0 | 0 | 1 | 0 | 180 | 144 | 1 | 180 | 6 | 216 | 3 | 187.2 | 15912 | 18720 | 28080
Reporting Scheduling Layer - Batch Scripting & Scheduling | 0 | 60 | 100 | 200 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Report Delivery Layer - EDDI/Content Manager/e-mail | 0 | 60 | 80 | 120 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Report Misc work items (bulk access, training) | 0 | 40 | 80 | 120 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Subtotal | [9 empty] | 406 | 324.8 |  | 406 |  | 487.2 |  | 422.24 | 35890.4 | 42224 | 63336
MDM / RDM
[5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
[5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
[5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
[5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
[5 empty] | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Subtotal | [9 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
DATA QUALITY (ATACCAMA)
Data Profiling | 10 | 22 | 44 | 66 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
DQD Validation with business rules | 22 | 43 | 73 | 103 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
DQ Enrichment | 33 | 65 | 106 | 167 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
DQ Standardization | 34 | 67 | 108 | 169 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
DQ Reconciliation | 68 | 137 | 266 | 401 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 0 | 6 | 0 | 0 | 0 | 0
Subtotal | [9 empty] | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0
TOTAL | [9 empty] | 586 | 468.8 |  | 586 |  | 703.2 |  | 609.44 | 51802.4 | 60944 | 91416

## Work Items
INFORMATICS - WORK ITEMS
Work Item / Story Card | Work Item Name | Description | Complixity Assumed | Other Assumptions
1 |  |  | Medium
2 |  |  | Simple
3 |  |  | Complex
4 |  |  | Complex
5 |  |  | Complex
6 |  |  | Complex
7 |  |  | Complex

## Platform - Storage & Compute
PLATFORM - STORAGE & COMPUTE
Layer >>>>> |  | JOB DURATION (Mins.) | RAW / DATA LAKE | STANDARD | AGGREGATED - HIVE | DISTRIBUTED - HIVE | DISTRIBUTED - REDSHIFT | DISTRIBUTED - POSTGRES | NON-PROD | PROD
Storage
Initial History / Current Year - EBS - GBs |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Initial History / Current Year - S3 - GBs |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Initial History / Current Year - HDFS - GBs |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
TOTAL Storage for Initial History / Current Year |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Normal Growth + Incremental : % per year |  |  | 120% | 120% | 120% | 120% | 120% | 120%
Normal Growth + Incremental : GB per year |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Compute
Number of Jobs | DAILY | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | DAILY | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | DAILY | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | DAILY | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | DAILY |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | WEEKLY | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | WEEKLY | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | WEEKLY | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | WEEKLY | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | WEEKLY |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | MONTHLY | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MONTHLY | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MONTHLY | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MONTHLY | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | MONTHLY |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | YEARLY | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | YEARLY | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | YEARLY | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | YEARLY | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | YEARLY |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | ADHOC | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | ADHOC | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | ADHOC | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | ADHOC | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | ADHOC |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | MICROBATCH | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MICROBATCH | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MICROBATCH | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | MICROBATCH | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | MICROBATCH |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Number of Jobs | REALTIME | 5 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | REALTIME | 10 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | REALTIME | 15 | 0 | 0 | 0 | 0 | 0 | 0
Number of Jobs | REALTIME | 30 | 0 | 0 | 0 | 0 | 0 | 0
Total Run Time (in hrs) | REALTIME |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Platform Support Tasks
New Schema required |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Service IDs required |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Approximate number of deployments |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Copy data from Production |  |  | YES | YES | NO | NO | NO | NO
New Bule Access Roles Required |  |  | YES | YES | YES | NO | NO | NO
New Bule Access Roles Required |  |  | YES | YES | YES | NO | NO | NO

## Platform - Hardware
Qty | Server Purpose | OS | CPU | Memory (GB) | Data (GB) | Comments
1 | Edge Node | RHEL | 8 | 128 | 300 | Sample Row - Do not Update
1 | RDP Server | Windows | 8 | 64 | 500 | Sample Row - Do not Update
2 | Tableau Server | RHEL | 4 | 32 | 100 | Sample Row - Do not Update
1 | Tableau Desktop | RHEL | 4 | 32 | 100 | Sample Row - Do not Update
1 | Web Server | RHEL | 4 | 16 | 100 | Sample Row - Do not Update
Qty | Server Purpose | OS | CPU | Memory (GB) | Data (GB) | Comments

## Platform - Software
Product Type | Number of Users/Licenses | Comments |  | Tableau Interactor/Viewer
Tableau Interactor/Viewer | 20 | SBP ###### | Sample Row - Do not Update | Tableau Publisher/Explorer
Tableau Publisher/Explorer | 2 | SBP ###### | Sample Row - Do not Update | Tableau Creator
Tableau Creator | 2 | SBP ###### | Sample Row - Do not Update | Tableau Publisher/Explorer
SAS | 2 | SBP ###### | Sample Row - Do not Update | Tableau Creator
SAS
Product Type | Number of Users/Licenses | Comments
Tableau Interactor/Viewer
Tableau Publisher/Explorer
Tableau Creator
SAS

## Data Engg - Resource Breakdown
DATA ENGINEERING - RESOURCE BREAKDOWN | [6 empty] | SUMMARY
EDW - DATA INTEGRATION - FOUNDATION | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX | TOTAL | ROLE | EFFORT
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0 | DATA ARCHITECT | 16
Analysis : Data Integration Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0 | DATA ANALYST | 48
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0 | TECH LEAD | 32
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0 | DATA ENGINEER | 80
Build : Data Integration Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0 | INFA ADMIN | 0
Test : Data Integration Code Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0 | DBA | 0
Build : Request EDDI (Data Engineer) | DATA ENGINEER | 0 | 0 | 0 | 0 | 0 | DEPLOYMENT ENGINEER | 4
Deploy : Deploy Code (INFA Admin) | INFA ADMIN | 0 | 0 | 0 | 0 | 0 | TOTAL | 180
Deploy : Deploy Code (DBA) | DBA | 0 | 0 | 0 | 0 | 0
EXTRACTION FROM DATABASES | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Extraction Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : Request EDDI (Data Engineer) | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (INFA Admin) | INFA ADMIN | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (DBA) | DBA | 0 | 0 | 0 | 0 | 0
RAW / DATA LAKE (easyETL) | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Ingestion Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Gather Metadata | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : DDL and Config Files | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : Scala/Spark Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : ABC Scripts | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Validate the record count and column values | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
RAW / DATA LAKE (Custom) | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Ingestion Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Gather Metadata | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : DDL and Config Files | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : Scala/Spark Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : ABC Scripts | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Validate the record count and column values | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
STANDARD | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Business Rules & Mapping | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Gather Metadata | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : DDL and Config Files | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : Scala/Spark Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : ABC Scripts | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Validate as per Business Rules | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
AGGREGATED | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 16 | 0 | 16
Analysis : Business Rules & Mapping | DATA ANALYST | 0 | 0 | 48 | 0 | 48
Oversight : Technical | TECH LEAD | 0 | 0 | 16 | 0 | 16
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 16 | 0 | 16
Build : Gather Metadata | DATA ENGINEER | 0 | 0 | 4 | 0 | 4
Build : DDL and Config Files | DATA ENGINEER | 0 | 0 | 10 | 0 | 10
Build : Scala/Spark Code | DATA ENGINEER | 0 | 0 | 44 | 0 | 44
Build : ABC Scripts | DATA ENGINEER | 0 | 0 | 2 | 0 | 2
Test : Validate as per Business Rules | DATA ENGINEER | 0 | 0 | 20 | 0 | 20
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 4 | 0 | 4
DISTRIBUTED | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Business Rules & Mapping | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Gather Metadata | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : DDL and Config Files | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : Scala/Spark Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Build : ABC Scripts | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Validate as per Business Rules | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
CUSTOM DATA EXTRACTION (FROM IE) | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Extraction Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
MULESOFT API | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Analysis : Extraction Rules | DATA ANALYST | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Design : Solution Design Documents | TECH LEAD | 0 | 0 | 0 | 0 | 0
Build : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Test : Extraction Code | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Deploy : Deploy Code (Deployment Engineer) | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0

## Reporting - Resource Breakdown
REPORTING & - RESSOURCE LEVEL BREAKDOWN | [5 empty] | SUMMARY
Reporting - Sematic Data Layer | ROLE | SIMPLE | MEDIUM | COMPLEX | TOTAL | ROLE | EFFORT
Architecture : Solution / Data | DATA ARCHITECT | 0 | 6 | 0 | 6 | DATA ARCHITECT | 8
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 24 | 0 | 24 | REPORT TECH LEAD | 19.9
Oversight : Technical | REPORT TECH LEAD | 0 | 3 | 0 | 3 | REPORT DEVELOPER | 358.2
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 6 | 0 | 6 | TABLEAU ADMIN | 10.95
Build : Semantic Layer | REPORT DEVELOPER | 0 | 18 | 0 | 18 | WEB ADMIN | 8.95
Test : Semantic Layer (DevOps) | REPORT DEVELOPER | 0 | 6 | 0 | 6 | TOTAL | 406
Deploy : Semantic Layer | TABLEAU ADMIN | 0 | 3 | 0 | 3
Reporting - Data Cubes | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Data Cubes | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test : Data Cubes (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Data Cubes | TABLEAU ADMIN | 0 | 0 | 0 | 0
Reporting Presentation Layer - Dashboard | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 1 | 0 | 1
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 31.8 | 0 | 31.8
Oversight : Technical | REPORT TECH LEAD | 0 | 7.95 | 0 | 7.95
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 15.9 | 0 | 15.9
Build : Dashboard | REPORT DEVELOPER | 0 | 79.5 | 0 | 79.5
Test : Dashboard (DevOps) | REPORT DEVELOPER | 0 | 15.9 | 0 | 15.9
Deploy : Dashboard | TABLEAU ADMIN | 0 | 7.95 | 0 | 7.95
Reporting Presentation Layer - Reports | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Reports | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test : Reports (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Reports | TABLEAU ADMIN | 0 | 0 | 0 | 0
Reporting Presentation Layer - Adhoc Report | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Adhoc Reports | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test : Adhoc Reports (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Adhoc Reports | TABLEAU ADMIN | 0 | 0 | 0 | 0
Reporting Web UI Customization | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 1 | 0 | 1
Analysis : Reporting Data | REPORT DEVELOPER | 0 | 17.9 | 0 | 17.9
Oversight : Technical | REPORT TECH LEAD | 0 | 8.95 | 0 | 8.95
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 17.9 | 0 | 17.9
Build : UI Web | REPORT DEVELOPER | 0 | 107.4 | 0 | 107.4
Test : UI Web (DevOps) | REPORT DEVELOPER | 0 | 17.9 | 0 | 17.9
Deploy : UI Web | WEB ADMIN | 0 | 8.95 | 0 | 8.95
Reporting Scheduling Layer - Batch Scripting & Scheduling | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Business Needs | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Scripts | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test : Scripts (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Scripts | TABLEAU ADMIN | 0 | 0 | 0 | 0
Report Delivery Layer - EDDI/Content Manager/e-mail | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Report Delivery Needs | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Delivery Channels | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test :Delivery Channels (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Delivery Channels | TABLEAU ADMIN | 0 | 0 | 0 | 0
Report Misc work items (bulk access, training) | ROLE | SIMPLE | MEDIUM | COMPLEX | COMPLEX
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0
Analysis : Traing and Access Data | REPORT DEVELOPER | 0 | 0 | 0 | 0
Oversight : Technical | REPORT TECH LEAD | 0 | 0 | 0 | 0
Design : Solution Design Documents | REPORT DEVELOPER | 0 | 0 | 0 | 0
Build : Access and Training | REPORT DEVELOPER | 0 | 0 | 0 | 0
Test : Access (DevOps) | REPORT DEVELOPER | 0 | 0 | 0 | 0
Deploy : Access and Training | TABLEAU ADMIN | 0 | 0 | 0 | 0

## Ataccama DQ - Resource Breakdow
ATACCMA DQ - RESOURCE BREAKDOWN | [6 empty] | SUMMARY
Data Profiling | ROLE | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX | TOTAL | ROLE | EFFORT
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0 | DATA ARCHITECT | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0 | TECH LEAD | 0
Ataccama Build& Test | ATACCAMA DEVELOPER | 0 | 0 | 0 | 0 | 0 | ATACCAMA DEVELOPER | 0
Data Engineer Support | DATA ENGINEER | 0 | 0 | 0 | 0 | 0 | DATA ENGINEER | 0
Platform Deployment Support | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0 | DEPLOYMENT ENGINEER | 0
DQD Validation with business rules | [6 empty] | TOTAL | 0
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Ataccama Build& Test | ATACCAMA DEVELOPER | 0 | 0 | 0 | 0 | 0
Data Engineer Support | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Platform Deployment Support | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
DQ Enrichment
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Ataccama Build& Test | ATACCAMA DEVELOPER | 0 | 0 | 0 | 0 | 0
Data Engineer Support | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Platform Deployment Support | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
DQ Standardization
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Ataccama Build& Test | ATACCAMA DEVELOPER | 0 | 0 | 0 | 0 | 0
Data Engineer Support | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Platform Deployment Support | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0
DQ Reconcilitation
Architecture : Solution / Data | DATA ARCHITECT | 0 | 0 | 0 | 0 | 0
Oversight : Technical | TECH LEAD | 0 | 0 | 0 | 0 | 0
Ataccama Build& Test | ATACCAMA DEVELOPER | 0 | 0 | 0 | 0 | 0
Data Engineer Support | DATA ENGINEER | 0 | 0 | 0 | 0 | 0
Platform Deployment Support | DEPLOYMENT ENGINEER | 0 | 0 | 0 | 0 | 0

## Data Engg - Standard Effort
DATA ENGINEERING - INGESTION & CUSTOM DATA FEEDS
STANDARD ESTIMATE PER FILE
| VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
EDW - Data Ingestion - Foundation | 40 | 160 | 240 | 360
Extraction from Databases / EDW - Custom Data Feeds | 20 | 120 | 180 | 300
Data Ingestion - Raw / Data Lake (easyETL) | 8 | 16 | 24 | 48
Data Ingestion - Raw / Data Lake (CUSTOM) | 40 | 100 | 160 | 200
Data Ingestion - Standard | 80 | 160 | 240 | 360
Data Ingestion - Aggregate | 80 | 120 | 180 | 280
Data Ingestion - Distribution | 80 | 100 | 140 | 240
Custom Data Extraction (From IE) | 40 | 160 | 260 | 360
MuleSoft API | 40 | 80 | 120 | 200
EDW - DATA INGESTION - FOUNDATION
Architecture : Solution / Data | 2 | 8 | 10 | 20
Analysis : Data Integration Rules | 2 | 60 | 80 | 120
Oversight : Technical | 4 | 16 | 20 | 32
Design : Solution Design Documents | 2 | 8 | 16 | 24
Build : Data Integration Code | 20 | 40 | 80 | 120
Test : Data Integration Code Code | 4 | 20 | 24 | 32
Build : Request EDDI (Data Engineer) | 2 | 2 | 2 | 2
Deploy : Deploy Code (INFA Admin) | 2 | 2 | 4 | 6
Deploy : Deploy Code (DBA) | 2 | 4 | 4 | 4
EXTRACTION FROM / CUSTOM DATA FEEDS
Architecture : Solution / Data | 0 | 8 | 16 | 24
Analysis : Extraction Rules | 0 | 10 | 40 | 120
Oversight : Technical | 1 | 20 | 24 | 32
Design : Solution Design Documents | 1 | 8 | 16 | 20
Build : Extraction Code | 8 | 48 | 52 | 64
Test : Extraction Code | 4 | 20 | 24 | 32
Build : Request EDDI (Data Engineer) | 2 | 2 | 2 | 2
Deploy : Deploy Code (INFA Admin) | 2 | 2 | 2 | 2
Deploy : Deploy Code (DBA) | 2 | 2 | 4 | 4
RAW / DATA LAKE (easyETL)
Architecture : Solution / Data | 0 | 1 | 2 | 4
Analysis : Ingestion Rules | 0 | 0 | 0 | 0
Oversight : Technical | 1 | 1 | 2 | 4
Design : Solution Design Documents | 1 | 2 | 2 | 4
Build : Gather Metadata | 1 | 2 | 3 | 6
Build : DDL and Config Files | 1 | 2 | 4 | 8
Build : Scala/Spark Code | 1 | 2 | 3 | 6
Build : ABC Scripts | 1 | 2 | 2 | 6
Test : Validate the record count and column values | 1 | 2 | 4 | 8
Deploy : Deploy Code (Deployment Engineer) | 1 | 2 | 2 | 2
RAW / DATA LAKE (Custom)
Architecture : Solution / Data | 2 | 8 | 16 | 24
Analysis : Ingestion Rules | 0 | 0 | 0 | 0
Oversight : Technical | 4 | 8 | 16 | 24
Design : Solution Design Documents | 2 | 16 | 32 | 40
Build : Gather Metadata | 4 | 2 | 4 | 6
Build : DDL and Config Files | 2 | 4 | 6 | 4
Build : Scala/Spark Code | 20 | 40 | 56 | 64
Build : ABC Scripts | 2 | 2 | 2 | 2
Test : Validate the record count and column values | 2 | 16 | 24 | 32
Deploy : Deploy Code (Deployment Engineer) | 2 | 4 | 4 | 4
STANDARD
Architecture : Solution / Data | 4 | 8 | 16 | 24
Analysis : Business Rules & Mapping | 24 | 32 | 60 | 120
Oversight : Technical | 8 | 8 | 16 | 24
Design : Solution Design Documents | 8 | 8 | 16 | 24
Build : Gather Metadata | 4 | 2 | 2 | 2
Build : DDL and Config Files | 4 | 4 | 8 | 8
Build : Scala/Spark Code | 20 | 80 | 92 | 120
Build : ABC Scripts | 1 | 2 | 2 | 2
Test : Validate as per Business Rules | 3 | 12 | 24 | 32
Deploy : Deploy Code (Deployment Engineer) | 4 | 4 | 4 | 4
AGGREGATED
Architecture : Solution / Data | 4 | 8 | 16 | 24
Analysis : Business Rules & Mapping | 24 | 40 | 48 | 72
Oversight : Technical | 8 | 8 | 16 | 24
Design : Solution Design Documents | 8 | 12 | 16 | 24
Build : Gather Metadata | 4 | 4 | 4 | 4
Build : DDL and Config Files | 4 | 8 | 10 | 12
Build : Scala/Spark Code | 20 | 24 | 44 | 82
Build : ABC Scripts | 1 | 2 | 2 | 2
Test : Validate as per Business Rules | 3 | 10 | 20 | 32
Deploy : Deploy Code (Deployment Engineer) | 4 | 4 | 4 | 4
DISTRIBUTION
Architecture : Solution / Data | 4 | 8 | 16 | 24
Analysis : Business Rules & Mapping | 24 | 32 | 40 | 80
Oversight : Technical | 8 | 8 | 12 | 16
Design : Solution Design Documents | 8 | 8 | 16 | 24
Build : Gather Metadata | 4 | 2 | 2 | 2
Build : DDL and Config Files | 4 | 8 | 8 | 8
Build : Scala/Spark Code | 20 | 24 | 32 | 64
Build : ABC Scripts | 1 | 2 | 2 | 2
Test : Validate as per Business Rules | 3 | 4 | 8 | 16
Deploy : Deploy Code (Deployment Engineer) | 4 | 4 | 4 | 4
CUSTOM DATA EXTRACTION (FROM IE)
Architecture : Solution / Data | 2 | 8 | 16 | 24
Analysis : Extraction Rules | 4 | 40 | 80 | 100
Oversight : Technical | 8 | 20 | 24 | 32
Design : Solution Design Documents | 4 | 8 | 16 | 20
Build : Extraction Code | 16 | 60 | 80 | 120
Test : Extraction Code | 4 | 20 | 40 | 60
Deploy : Deploy Code (Deployment Engineer) | 2 | 4 | 4 | 4
MULESOFT API
Architecture : Solution / Data | 2 | 4 | 6 | 8
Analysis : Mapping Rules | 8 | 16 | 24 | 48
Oversight : Technical | 4 | 8 | 12 | 16
Design : Solution Design Documents | 4 | 8 | 12 | 16
Build : MuleSoft API | 16 | 32 | 48 | 64
Test : MuleSoft API | 4 | 8 | 12 | 40
Deploy : Deploy Code (Deployment Engineer) | 2 | 4 | 6 | 8

## Reporting - Standard Effort
REPORTING & ANALYTICS
STANDARD ESTIMATE PER FILE
| SIMPLE | MEDIUM | COMPLEX
Reporting - Sematic Data Layer | 44 | 66 | 88
Reporting - Data Cubes | 130 | 180 | 260
Reporting Presentation Layer - Dashboard | 130 | 160 | 180
Reporting Presentation Layer - Reports | 110 | 130 | 150
Reporting Presentation Layer - Adhoc Report | 60 | 80 | 100
Reporting Web UI Customization | 100 | 180 | 260
Reporting Scheduling Layer - Batch Scripting & Scheduling | 60 | 100 | 200
Report Delivery Layer - EDDI/Content Manager/e-mail | 60 | 80 | 120
Report Misc work items (bulk access, training) | 40 | 80 | 120
Reporting - Sematic Data Layer
Architecture : Solution / Data | 4 | 6 | 8
Analysis : Reporting Data | 16 | 24 | 32
Oversight : Technical | 2 | 3 | 4
Design : Solution Design Documents | 4 | 6 | 8
Build : Semantic Layer | 12 | 18 | 24
Test : Semantic Layer (DevOps) | 4 | 6 | 8
Deploy : Semantic Layer | 2 | 3 | 4
Reporting - Data Cubes
Architecture : Solution / Data | 30 | 40 | 60
Analysis : Reporting Data | 41 | 57 | 80
Oversight : Technical | 5 | 7 | 10
Design : Solution Design Documents | 10 | 14 | 20
Build : Data Cubes | 30 | 42 | 60
Test : Data Cubes (DevOps) | 10 | 14 | 20
Deploy : Data Cubes | 4 | 6 | 10
Reporting Presentation Layer - Dashboard
Architecture : Solution / Data | 1 | 1 | 1
Analysis : Reporting Data | 25.8 | 31.8 | 35.8
Oversight : Technical | 6.45 | 7.95 | 8.95
Design : Solution Design Documents | 12.9 | 15.9 | 17.9
Build : Dashboard | 64.5 | 79.5 | 89.5
Test : Dashboard (DevOps) | 12.9 | 15.9 | 17.9
Deploy : Dashboard | 6.45 | 7.95 | 8.95
Reporting Presentation Layer - Reports
Architecture : Solution / Data | 1 | 1 | 1
Analysis : Reporting Data | 21.8 | 25.8 | 29.8
Oversight : Technical | 5.45 | 6.45 | 7.45
Design : Solution Design Documents | 10.9 | 12.9 | 14.9
Build : Reports | 54.5 | 64.5 | 74.5
Test : Reports (DevOps) | 10.9 | 12.9 | 14.9
Deploy : Reports | 5.45 | 6.45 | 7.45
Reporting Presentation Layer - Adhoc Report
Architecture : Solution / Data | 1 | 1 | 1
Analysis : Reporting Data | 17.7 | 23.7 | 29.7
Oversight : Technical | 2.95 | 3.95 | 4.95
Design : Solution Design Documents | 5.9 | 7.9 | 9.9
Build : Adhoc Reports | 23.6 | 31.6 | 39.6
Test : Adhoc Reports (DevOps) | 5.9 | 7.9 | 9.9
Deploy : Adhoc Reports | 2.95 | 3.95 | 4.95
Reporting Web UI Customization
Architecture : Solution / Data | 1 | 1 | 1
Analysis : Reporting Data | 9.9 | 17.9 | 25.9
Oversight : Technical | 4.95 | 8.95 | 12.95
Design : Solution Design Documents | 9.9 | 17.9 | 25.9
Build : UI Web | 59.4 | 107.4 | 155.4
Test : UI Web (DevOps) | 9.9 | 17.9 | 25.9
Deploy : UI Web | 4.95 | 8.95 | 12.95
Reporting Scheduling Layer - Batch Scripting & Scheduling
Architecture : Solution / Data | 1 | 1 | 1
Analysis : Business Needs | 11.8 | 19.8 | 39.8
Oversight : Technical | 2.95 | 4.95 | 9.95
Design : Solution Design Documents | 5.9 | 9.9 | 19.9
Build : Scripts | 29.5 | 49.5 | 99.5
Test : Scripts (DevOps) | 5.9 | 9.9 | 19.9
Deploy : Scripts | 2.95 | 4.95 | 9.95
Report Delivery Layer - EDDI/Content Manager/e-mail
Architecture : Solution / Data | 0 | 0 | 0
Analysis : Report Delivery Needs | 6 | 8 | 12
Oversight : Technical | 3 | 4 | 6
Design : Solution Design Documents | 6 | 8 | 12
Build : Delivery Channels | 36 | 48 | 72
Test :Delivery Channels (DevOps) | 6 | 8 | 12
Deploy : Delivery Channels | 3 | 4 | 6
Report Misc work items (bulk access, training)
Architecture : Solution / Data | 0 | 0 | 0
Analysis : Traing and Access Data | 4 | 8 | 12
Oversight : Technical | 2 | 4 | 6
Design : Solution Design Documents | 4 | 8 | 12
Build : Access and Training | 20 | 40 | 60
Test : Access (DevOps) | 8 | 16 | 24
Deploy : Access and Training | 2 | 4 | 6

## Ataccama DQ - Standard Effort
ATACCAMA DQ
STANDARD ESTIMATE
| VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
Data Profiling | 10 | 22 | 44 | 66
DQD Validation with business rules | 22 | 43 | 73 | 103
DQ Enrichment | 33 | 65 | 106 | 167
DQ Standardization | 34 | 67 | 108 | 169
DQ Reconcilitation | 68 | 137 | 266 | 401
Data Profiling
Architecture : Solution / Data | 1 | 2 | 4 | 6
Oversight : Technical | 0 | 0 | 0 | 0
Ataccama Build& Test | 1 | 5 | 10 | 15
Data Engineer Support | 0 | 0 | 0 | 0
Platform Deployment Support | 8 | 15 | 30 | 45
DQD Validation with business rules
Architecture : Solution / Data | 1 | 2 | 4 | 6
Oversight : Technical | 2 | 4 | 6 | 8
Ataccama Build& Test | 10 | 20 | 30 | 40
Data Engineer Support | 1 | 2 | 3 | 4
Platform Deployment Support | 8 | 15 | 30 | 45
DQ Enrichment
Architecture : Solution / Data | 1 | 2 | 4 | 6
Oversight : Technical | 2 | 4 | 6 | 8
Ataccama Build& Test | 20 | 40 | 60 | 100
Data Engineer Support | 2 | 4 | 6 | 8
Platform Deployment Support | 8 | 15 | 30 | 45
DQ Standardization
Architecture : Solution / Data | 2 | 4 | 6 | 8
Oversight : Technical | 2 | 4 | 6 | 8
Ataccama Build& Test | 20 | 40 | 60 | 100
Data Engineer Support | 2 | 4 | 6 | 8
Platform Deployment Support | 8 | 15 | 30 | 45
DQ Reconcilitation
Architecture : Solution / Data | 2 | 6 | 16 | 24
Oversight : Technical | 4 | 8 | 8 | 16
Ataccama Build& Test | 50 | 100 | 200 | 300
Data Engineer Support | 4 | 8 | 12 | 16
Platform Deployment Support | 8 | 15 | 30 | 45

## Data Engg - Complexity Factors
INFORMATICS - DATA ENGINEERING - COMPLEXITY FACTORS
COMPLEXITY >>>>>> | VERY SIMPLE | SIMPLE | MEDIUM | COMPLEX
EXTRACTION FROM DATABASES | One time data extract | 1 Table Straight Moves Complete Dump each time | 1 Table Straight Moves Requires Incremental logics to be applied | 2 or more tables involved Transformaiton rules to be applied Required incremental logics to be applied
INGESTION - RAW / DATA LAKE (easyETL) | One time data ingestion OR Metadata is available witin BCBSM Changes to the existing feeds and history extact | EasyETL Framework can be used Metadata has to be provided by external sources < 100 Fields | EasyETL Framework can be used Metadata has to be provided by external sources > 100 and < 200 Fields | EasyETL Framework can be used Metadata has to be provided by external sources > 200 Fields
INGESTION - RAW / DATA LAKE (Custom) | One time data ingestion Changes to the existing feeds and history extact | Structured Data Delimted Files with header or trailer Custom Code needs to be built | Structured Data Fixed Width Files Custom Code needs to be built | Unstructured Data Real Time or Micro Batch Custom Code needs to be built
INGESTION - STANDARD | < 100 Fields No transformations Changes to the existing feeds and history load | < 100 Fields < 5 Transformations | > 100 Fields and < 200 Fields > 5 and < 10 Transformations | > 200 Fields OR > 20 Transformations OR Member Matching or Provider Matching
INGESTION - AGGREGATE | < 100 Fields No transformations Changes to the existing feeds and history load | < 100 Fields < 5 Transformations < Aggregates Involved | > 100 Fields and < 200 Fields > 5 and < 10 Transformations < Aggregates Involved | > 200 Fields OR > 20 Transformations < Aggregates Involved
INGESTION - DISTRIBUTION | < 100 Fields No transformations Changes to the existing feeds and history load | < 100 Fields < 5 Transformations | > 100 Fields and < 200 Fields > 5 and < 10 Transformations | > 200 Fields OR > 20 Transformations
EXTRACTION FROM IE (CUSTOM FEEDS) | One time extraction with SQL provided Changes to the existing feeds and history load | < 20 Business Rules <= 100 Fields | >= 20 Business Rules AND < 50 Business Rules > 100 Fields AND < 500 Fields | > 50 Business Rules > 500 Fields

## Reporting - Complexity Factors
Reporting Data Layer - Semantic Layer
1. Simple: Straight forward 1:1 mapping with small table with <10 fields
2. Medium: Medium tables with 10-20 fields. Simple calculations/filters involved and associated data analysis needed
3. Complex: Multiple tables and data blending needed at Tableau. More calculations and filters/ prompt page involved
Reporting Data Layer - Data Cubes
1. Simple: Straight forward 1:1 mapping with small table with <10 fields
2. Medium: Medium tables with 10-20 fields. Simple calculations/filters involved and associated data analysis needed
3. Complex: Multiple tables and data blending needed at Tableau. More calculations and filters/ prompt page involved
Reporting Presentation Layer - Adhoc/Reports/Dashboard
1. Simple: Reporting fields <10 and straight forward report real estate planning
2. Medium: 10-20 reporitng fields. More detailed real estate planning is needed
3. Complex: more than 20 fields and some creative design is needed to accommodate reporing real estate
Reporting Batch Scripting & Scheduling
1. Simple: Just reuse of existing batch scripts - Straight forward and simple coding to pull a report and dispatch
2. Medium: integrate with config data table and some intelligence built in the batch scripts
3. Complex: Python coding to do report format changes in the batch script itself
Reporting Batch Scripting & Scheduling
1. Simple: Just reuse of existing batch scripts - Straight forward and simple coding to pull a report and dispatch
2. Medium: integrate with config data table and some intelligence built in the batch scripts
3. Complex: Python coding to do report format changes in the batch script itself
Reporting EDDI/Content Manager/E-mail
1. Simple: Just the EDDI setup help
2. Medium: In additional EDDI, do work for content manager or EOS configurations
3. Complex: E-mail dispath configurations
Reporting Web UI customizations
1. Simple: simple single screen customization - straight forward pull of reports
2. Medium: 2-3 screen customization with some navigation logic
3. Complex: More complex UI navigation and intelligence. External library integrations like excel work book extract etc
Reporting Misc Items
1. Simple: Few business users (2-3)
2. Medium: 4-10 users
3. Complex: More than 10 users

## Data Engg - Checklist
INFORMATICS - DATA ENGINEERING - QUESTIONS FOR ESTIMATES
EXTRACTION FROM DATABASES
INGESTION - RAW / DATA LAKE (easyETL)
INGESTION - RAW / DATA LAKE (Custom)
INGESTION - STANDARD
INGESTION - AGGREGATE
INGESTION - DISTRIBUTION
EXTRACTION FROM IE (CUSTOM FEEDS)
MULESOFT API

## General Assumptions
General Assumptions
DevOps is assumed for the estimate (DEV Team does the Unit Testing and SIT)
ITTO Estimation is not included in this estimate
Non-Labor cost is provded by the Platform Team

## Template Version
Version Number | Comments | Date
1 | Initial Template | 2020-02-23
2 | Summary Table in Resource Breakdown, Reporting & Analytics - Revised Effort | 2020-05-19